## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | Visibility | SortOrder
1 | Extension Pre-Submission | EAC Extension | EA Act (2018) | 60 | FALSE | #FFFFFF | REGULAR | 1
2 | Extension Submission Review | EAC Extension | EA Act (2018) | 180 | FALSE | #FFFFFF | REGULAR | 2
3 | Extension Decision | EAC Extension | EA Act (2018) | 30 | FALSE | #FFFFFF | REGULAR | 3

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | EventPosition | MultipleDays | StartAt | NumberOfDays | Visibility | SortOrder
1 |  | 1 | Initial Discussion with Holder | Extension Pre-Submission | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 1
2 |  | 1 | Holder starts engagement with First Nations | Extension Pre-Submission | Generic | Milestone | INTERMEDIATE | FALSE | 14 | 0 | SUGGESTED | 2
3 |  | 1 | Submit Estimate for Capacity Funding | Extension Pre-Submission | Capacity Funding | Finance | INTERMEDIATE | FALSE | 45 | 0 | SUGGESTED | 3
4 | 3 | 1 | Rough Estimate for Capacity Funding Due | Extension Pre-Submission | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 4
5 |  | 1 | Additional Information Submission | Extension Pre-Submission | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 5
6 |  | 1 | Meeting with Holder | Extension Pre-Submission | Meeting | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 6
7 |  | 1 | Direct Submission of EAC Extension Request - DELETE this Pre-Submission Phase! | Extension Pre-Submission | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 7
8 |  | 1 | Document Submitted to EAO for "Initial Review" | Extension Pre-Submission | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 8
9 | 8 | 1 | EAO's Viewpoint on Submitted Document | Extension Pre-Submission | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 10 | 0 | OPTIONAL | 9
10 |  | 1 | EAC Extension Required Decision | Extension Pre-Submission | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 10
11 |  | 1 | EAC Extension Request Withdrawn | Extension Pre-Submission | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 11
12 |  | 1 | Other | Extension Pre-Submission | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 12
13 |  | 1 | Last day of Pre-Submission (day before EAC Extension Request submitted) | Extension Pre-Submission | Date Capture | Milestone | END | FALSE | 60 | 0 | MANDATORY | 13
14 |  | 2 | EAC Extension Request Submission Received | Extension Submission Review | Submission | Milestone | START | FALSE | 0 | 0 | MANDATORY | 14
15 | 14 | 2 | EAC Extension Requested Announcement & Tweet | Extension Submission Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 15
16 | 14 | 2 | EAC Extension Requested Milestone Bullet | Extension Submission Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 16
17 |  | 2 | EAC Extension Request Submission Circulated to FNs & TAC | Extension Submission Review | Generic | Milestone | INTERMEDIATE | FALSE | 7 | 0 | SUGGESTED | 17
18 |  | 2 | Confirm Capacity Funding Amounts | Extension Submission Review | Capacity Funding | Finance | INTERMEDIATE | FALSE | 14 | 0 | SUGGESTED | 18
19 | 18 | 2 | EAC Extension Capacity Funding Confirmation Due | Extension Submission Review | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 19
20 |  | 2 | Fee Order: Submission of EAC Extension Request | Extension Submission Review | Fee Order | Finance | INTERMEDIATE | FALSE | 30 | 0 | MANDATORY | 20
21 | 20 | 2 | Fee Order for Filing of EAC Extension Request | Extension Submission Review | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 21
22 |  | 2 | Draft EAC Extension Request Report | Extension Submission Review | Report | Milestone | INTERMEDIATE | FALSE | 120 | 0 | SUGGESTED | 22
23 |  | 2 | EAC Extension Request Report | Extension Submission Review | Report | Milestone | INTERMEDIATE | FALSE | 170 | 0 | MANDATORY | 23
24 |  | 2 | Additional Information Submission | Extension Submission Review | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 24
25 |  | 2 | Document Submitted to EAO for "Initial Review" | Extension Submission Review | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 25
26 | 25 | 2 | EAO's Viewpoint on Submitted Document | Extension Submission Review | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 10 | 0 | OPTIONAL | 26
27 |  | 2 | EAC Extension Required Decision | Extension Submission Review | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 27
28 |  | 2 | Comment Period | Extension Submission Review | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | 28
29 | 28 | 2 | PCP Coming Soon Announcement & Tweet | Extension Submission Review | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 29
30 | 28 | 2 | PCP Milestone Bullet | Extension Submission Review | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 30
31 | 28 | 2 | PCP Now Open Announcement & Tweet | Extension Submission Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 31
32 | 28 | 2 | PCP Ending Soon Announcement & Tweet | Extension Submission Review | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | 32
33 |  | 2 | Open House | Extension Submission Review | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 33
34 |  | 2 | Virtual Information Session | Extension Submission Review | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 34
35 |  | 2 | Comment Period Time Limit Extension | Extension Submission Review | PCP Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 35
36 | 35 | 2 | PCP Extended Announcement & Tweet | Extension Submission Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 36
37 | 35 | 2 | PCP Extended Milestone Bullet | Extension Submission Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 37
38 |  | 2 | EAC Extension Request Withdrawn | Extension Submission Review | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 38
39 | 38 | 2 | EAC Extension Request Withdrawal Announcement & Tweet | Extension Submission Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 39
40 | 38 | 2 | EAC Extension Request Withdrawn Milestone Bullet | Extension Submission Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 40
41 |  | 2 | Other | Extension Submission Review | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 41
42 |  | 2 | EAC Extension Decision Package Referred to CEAO | Extension Submission Review | Referral | Milestone | END | FALSE | 180 | 0 | MANDATORY | 42
43 |  | 3 | EAC Extension Decision Package Received by CEAO | Extension Decision | Generic | Milestone | START | FALSE | 0 | 0 | MANDATORY | 43
44 |  | 3 | Additional Information Submission | Extension Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 44
45 |  | 3 | EAC Extension Request Withdrawn | Extension Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 45
46 | 45 | 3 | EAC Extension Request Withdrawal Announcement & Tweet | Extension Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 46
47 | 45 | 3 | EAC Extension Request Withdrawn Milestone Bullet | Extension Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 47
48 |  | 3 | Other | Extension Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 48
49 |  | 3 | CEAO's EAC Extension Decision | Extension Decision | CEAO | Decision | END | FALSE | 30 | 0 | MANDATORY | 49
50 | 49 | 3 | EAC Extension Decision Announcement & Tweet | Extension Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 50
51 | 49 | 3 | EAC Extension Decision Milestone Bullet | Extension Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 51
52 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 52
53 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 53
54 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 54
55 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 55
56 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 56
57 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 57
58 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 58
59 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 59
60 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 60
61 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 61
62 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 62
63 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 63
64 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 64
65 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 65
66 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 66
67 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 67
68 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 68
69 | [6 empty] | INTERMEDIATE | FALSE | 0 | 0 |  | 69

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | SortOrder
1 | 7 | Direct Submission of EAC Extension Request - DELETE this Pre-Submission Phase! | Delete this "Extension Pre-Submission" and go directly to "Extension Submission Review" | 1
2 | 9 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is POSITIVE | 2
3 | 9 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is NEGATIVE | 3
4 | 10 | EAC Extension Required Decision | Switch to a Substantial Start Decision | 4
5 | 10 | EAC Extension Required Decision | Switch to an EAC Cancellation | 5
6 | 11 | EAC Extension Request Withdrawn | Proponent withdraws Submission from the EAC Extension process | 6
7 | 26 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is POSITIVE | 7
8 | 26 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is NEGATIVE | 8
9 | 27 | EAC Extension Required Decision | Switch to a Substantial Start Decision | 9
10 | 27 | EAC Extension Required Decision | Switch to an EAC Cancellation | 10
11 | 38 | EAC Extension Request Withdrawn | Proponent withdraws Submission from the EAC Extension process | 11
12 | 45 | EAC Extension Request Withdrawn | Proponent withdraws Submission from the EAC Extension process | 12
13 | 49 | CEAO's EAC Extension Decision | CEAO Extends the EAC | 13
14 | 49 | CEAO's EAC Extension Decision | CEAO Refuse's to Extend the EAC | 14

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 1 | Delete this "Extension Pre-Submission" and go directly to "Extension Submission Review" | SetEventDate | Set "Extension Submission Review ¦ EAC Extension Request Submission Received" ANTICIPATED to thisWorkStartDate | {"phase_name":"Extension Submission Review","work_type_id": 9, "ea_act_id": 3, "event_name": "EAC Extension Request Submission Received", "start_at": 0 } | 1
2 | 1 | Delete this "Extension Pre-Submission" and go directly to "Extension Submission Review" | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 2
3 | 1 | Delete this "Extension Pre-Submission" and go directly to "Extension Submission Review" | SetPhasesStatus | Set thisPhase to INACTIVE | [{"phase_name":"Extension Pre-Submission","work_type_id": 9, "ea_act_id": 3, "is_active": false }] | 3
4 | 2 | EAO's Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 4
5 | 3 | EAO's Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 5
6 | 4 | Switch to a Substantial Start Decision | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 6
7 | 4 | Switch to a Substantial Start Decision | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 7
8 | 4 | Switch to a Substantial Start Decision | SetWorkState | Set workState to CLOSED | {"work_state": "CLOSED"} | 8
9 | 4 | Switch to a Substantial Start Decision | NONE | Create a new WORK: "Substantial Start Decision" and link to thisWorkLinkedProject | {} | 9
10 | 5 | Switch to an EAC Cancellation | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 10
11 | 5 | Switch to an EAC Cancellation | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 11
12 | 5 | Switch to an EAC Cancellation | SetWorkState | Set workState to CLOSED | {"work_state": "CLOSED"} | 12
13 | 5 | Switch to an EAC Cancellation | NONE | Create a new WORK: "EAC Cancellation" and link to thisWorkLinkedProject | {} | 13
14 | 6 | Proponent withdraws Submission from the EAC Extension process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 14
15 | 6 | Proponent withdraws Submission from the EAC Extension process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 15
16 | 6 | Proponent withdraws Submission from the EAC Extension process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 16
17 | 7 | EAO's Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 17
18 | 8 | EAO's Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 18
19 | 9 | Switch to a Substantial Start Decision | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 19
20 | 9 | Switch to a Substantial Start Decision | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 20
21 | 9 | Switch to a Substantial Start Decision | SetWorkState | Set workState to CLOSED | {"work_state": "CLOSED"} | 21
22 | 9 | Switch to a Substantial Start Decision | NONE | Create a new WORK: "Substantial Start Decision" and link to thisWorkLinkedProject | {} | 22
23 | 10 | Switch to an EAC Cancellation | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 23
24 | 10 | Switch to an EAC Cancellation | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 24
25 | 10 | Switch to an EAC Cancellation | SetWorkState | Set workState to CLOSED | {"work_state": "CLOSED"} | 25
26 | 10 | Switch to an EAC Cancellation | NONE | Create a new WORK: "EAC Cancellation" and link to thisWorkLinkedProject | {} | 26
27 | 11 | Proponent withdraws Submission from the EAC Extension process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 27
28 | 11 | Proponent withdraws Submission from the EAC Extension process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 28
29 | 11 | Proponent withdraws Submission from the EAC Extension process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 29
30 | 12 | Proponent withdraws Submission from the EAC Extension process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 30
31 | 12 | Proponent withdraws Submission from the EAC Extension process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 31
32 | 12 | Proponent withdraws Submission from the EAC Extension process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 32
33 | 13 | CEAO Extends the EAC | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 33
34 | 13 | CEAO Extends the EAC | NONE | In the future this action should update the EAC CertificateEndDate | {} | 34
35 | 14 | CEAO Refuse's to Extend the EAC | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 35
36 | 14 | CEAO Refuse's to Extend the EAC | NONE | In the future this action should FLAG the EAC CertificateEndDate | {} | 36

## Lookups
WorkType | EA Act | Legislated |  | Event Type | Event Category | Visibility | ActionName | Event Position | Multiple Days | Action Name
Project Notification | EA Act (2018) | TRUE | Milestone | Generic | Milestone | MANDATORY | AllEventsDeactivated | START | TRUE | AddEvent
Minister's Designation | EA Act (2002) | FALSE | Milestone | Meeting | Calendar | SUGGESTED | AllEventsDeleted | INTERMEDIATE | FALSE | AddPhase
CEAO's Designation | EA Act (1996) |  | Milestone | Notification | Decision | OPTIONAL | CloseEverything | END |  | ChangePhaseEndEvent
EAC Assessment |  |  | Milestone | Order | Finance | HIDDEN | CloseWork |  |  | CreateWork
Exemption Request |  |  | Milestone | Referral | PCP |  | CompleteCurrentPhase |  |  | LockWorkStartDate
Dispute Resolution |  |  | Milestone | Report | Extension |  | CreateNewWork |  |  | SetEventDate
EAC/Order Amendment |  |  | Milestone | Request | Suspension |  | DisableWorkStartDate |  |  | SetEventStatus
Document Review |  |  | Milestone | Submission |  |  | DuplicatePhase |  |  | SetFederalInvolvement
EAC Extension |  |  | Milestone | Other | [5 empty] | SetPhaseStatus
Substantial Start Decision |  |  | Milestone | Date Capture | [5 empty] | SetProjectState
EAC/Order Transfer |  |  | Extension | Time Limit Extension | [5 empty] | SetProjectStatus
EAC/Order Suspension |  |  | Extension | PCP Time Limit Extension | [5 empty] | SetWorkDecisionMaker
EAC/Order Cancellation |  |  | Suspension | Time Limit Suspension | [5 empty] | SetWorkState
Other |  |  | Suspension | Time Limit Resumption
|  |  | Decision | EAC Ministers
|  |  | Decision | Minister
|  |  | Decision | CEAO
|  |  | Decision | ADM
|  |  | Decision | EPD
|  |  | Decision | PAD (Lead)
|  |  | Decision | Reviewer
|  |  | Decision | Federal
|  |  | Decision | Other
|  |  | PCP | Comment Period
|  |  | PCP | Open House
|  |  | PCP | Virtual Information Session
|  |  | PCP | Other
|  |  | Calendar | Communications
|  |  | Calendar | Executive
|  |  | Calendar | Financial
|  |  | Calendar | Work
|  |  | Calendar | Other
|  |  | Finance | Capacity Funding
|  |  | Finance | Fee Order
|  |  | Finance | Penalties
|  |  | Finance | Administrative
|  |  | Finance | Other