## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | Visibility | SortOrder | DayZero
1 | SubStart Pre-Assessment | Substantial Start Determination | EA Act (2018) | 60 | FALSE | #FFFFFF | REGULAR | 1 | TRUE
2 | SubStart Assessment | Substantial Start Determination | EA Act (2018) | 270 | FALSE | #FFFFFF | REGULAR | 2 | TRUE
3 | SubStart Decision | Substantial Start Determination | EA Act (2018) | 30 | FALSE | #FFFFFF | REGULAR | 3 | TRUE

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | EventPosition | MultipleDays | StartAt | NumberOfDays | Visibility | SortOrder
1 |  | 1 | Pre-Submission Starts (Holder Request, C&E Report, Date Confirmation, etc.) | SubStart Pre-Assessment | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 1
2 |  | 1 | Initiation Method of SubStart Determination | SubStart Pre-Assessment | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 7 | 0 | MANDATORY | 2
3 |  | 1 | SubStart Initiation Decision | SubStart Pre-Assessment | EPD | Decision | INTERMEDIATE | FALSE | 30 | 0 | MANDATORY | 3
4 |  | 1 | Additional Information Submission | SubStart Pre-Assessment | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 4
5 |  | 1 | Meeting with Holder | SubStart Pre-Assessment | Meeting | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 5
6 |  | 1 | Direct Submission of SubStart Determination Request - DELETE this SubStart Initiation Phase! | SubStart Pre-Assessment | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 6
7 |  | 1 | Request C&E Inspection | SubStart Pre-Assessment | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 7
8 |  | 1 | Document Submitted to EAO for "Initial Review" | SubStart Pre-Assessment | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 8
9 | 8 | 1 | EAO's Viewpoint on Submitted Document | SubStart Pre-Assessment | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 9
10 |  | 1 | EAC Extension Required | SubStart Pre-Assessment | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 10
11 |  | 1 | EAC Cancellation Required | SubStart Pre-Assessment | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 11
12 |  | 1 | Delegation of SubStart Decision to Minister | SubStart Pre-Assessment | Minister | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 12
13 |  | 1 | SubStart Determination Request Withdrawn | SubStart Pre-Assessment | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 13
14 |  | 1 | Other | SubStart Pre-Assessment | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 14
15 |  | 1 | Last day of Pre-Assessment (day before SubStart Assessment starts) | SubStart Pre-Assessment | Date Capture | Milestone | END | FALSE | 60 | 0 | MANDATORY | 15
16 |  | 2 | SubStart Assessment Started | SubStart Assessment | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 16
17 |  | 2 | Publish SubStart Request (Holder Initiated SubStart only) | SubStart Assessment | Generic | Milestone | INTERMEDIATE | FALSE | 30 | 0 | SUGGESTED | 17
18 |  | 2 | SubStart Request Circulated to FNs (Holder Initiated SubStart only) | SubStart Assessment | Generic | Milestone | INTERMEDIATE | FALSE | 60 | 0 | SUGGESTED | 18
19 |  | 2 | SubStart Determination Report | SubStart Assessment | Report | Milestone | INTERMEDIATE | FALSE | 250 | 0 | MANDATORY | 19
20 |  | 2 | Additional Information Submission | SubStart Assessment | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 20
21 |  | 2 | Document Submitted to EAO for "Initial Review" | SubStart Assessment | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 21
22 | 21 | 2 | EAO's Viewpoint on Submitted Document | SubStart Assessment | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 22
23 |  | 2 | Request C&E Inspection | SubStart Assessment | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 23
24 |  | 2 | EAC Extension Required | SubStart Assessment | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 24
25 |  | 2 | EAC Cancellation Required | SubStart Assessment | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 25
26 |  | 2 | Comment Period | SubStart Assessment | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | 26
27 | 26 | 2 | PCP Coming Soon Announcement & Tweet | SubStart Assessment | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 27
28 | 26 | 2 | PCP Milestone Bullet | SubStart Assessment | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 28
29 | 26 | 2 | PCP Now Open Announcement & Tweet | SubStart Assessment | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 29
30 | 26 | 2 | PCP Ending Soon Announcement & Tweet | SubStart Assessment | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | 30
31 |  | 2 | Open House | SubStart Assessment | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 31
32 |  | 2 | Virtual Information Session | SubStart Assessment | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 32
33 |  | 2 | Comment Period Time Limit Extension | SubStart Assessment | PCP Time Limit Extension | Extension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 33
34 | 33 | 2 | PCP Extended Announcement & Tweet | SubStart Assessment | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 34
35 | 33 | 2 | PCP Extended Milestone Bullet | SubStart Assessment | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 35
36 |  | 2 | Delegation of SubStart Decision to Minister | SubStart Assessment | Minister | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 36
37 | 37 | 2 | SubStart Determination Request Withdrawn | SubStart Assessment | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 37
38 | 37 | 2 | SubStart Determination Withdrawn Announcement & Tweet | SubStart Assessment | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 38
39 | 37 | 2 | SubStart Determination Withdrawn Milestone Bullet | SubStart Assessment | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 39
40 |  | 2 | Other | SubStart Assessment | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 40
41 |  | 2 | SubStart Determination Decision Package Referred to Decision Maker | SubStart Assessment | Referral | Milestone | END | FALSE | 270 | 0 | MANDATORY | 41
42 |  | 3 | SubStart Determination Decision Package Received | SubStart Decision | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 42
43 |  | 3 | Additional Information Submission | SubStart Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 43
44 |  | 3 | SubStart Determination Request Withdrawn | SubStart Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 44
45 | 44 | 3 | SubStart Determination Withdrawn Announcement & Tweet | SubStart Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 45
46 | 44 | 3 | SubStart Determination Withdrawn Milestone Bullet | SubStart Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 46
47 |  | 3 | Other | SubStart Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 47
48 |  | 3 | SubStart Determination Decision | SubStart Decision | CEAO | Decision | END | FALSE | 0 | 0 | MANDATORY | 48
49 | 48 | 3 | SubStart Determination Announcement & Tweet | SubStart Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 49
50 | 48 | 3 | SubStart Determination Milestone Bullet | SubStart Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 50
51 | [11 empty] | 51
52 | [11 empty] | 52
53 | [11 empty] | 53
54 | [11 empty] | 54
55 | [11 empty] | 55
56 | [11 empty] | 56
57 | [11 empty] | 57
58 | [11 empty] | 58
59 | [11 empty] | 59
60 | [11 empty] | 60
61 | [11 empty] | 61
62 | [11 empty] | 62
63 | [11 empty] | 63
64 | [11 empty] | 64
65 | [11 empty] | 65
66 | [11 empty] | 66
67 | [11 empty] | 67
68 | [11 empty] | 68
69 | [11 empty] | 69

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | OutcomeDescription | SortOrder
1 | 2 | Initiation Method of SubStart Determination | SubStart Initiated by Holder | The Substantial Start Determination is requested by the Holder | 1
2 | 2 | Initiation Method of SubStart Determination | SubStart Initiated by C&E/Other | The Substantial Start Determination is initiated by C&E or Other reporting the PROJECT in operation | 2
3 | 2 | Initiation Method of SubStart Determination | SubStart Initiated by Deadline | The Substantial Start Determination is initiated by an approaching EAC deadline | 3
4 | 3 | SubStart Initiation Decision | SubStart Determination is Not Needed | The EAO decides that the Substantial Start Determination is NOT NEEDED | 4
5 | 3 | SubStart Initiation Decision | SubStart Determination is Needed | The EAO decides that the Substantial Start Determination is NEEDED | 5
6 | 6 | Direct Submission of SubStart Determination Request - DELETE this SubStart Initiation Phase! | Delete the Pre-Assessment PHASE | Delete the "SubStart Pre-Assessment" PHASE and go directly to "SubStart Assessment" | 6
7 | 9 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is POSITIVE | EAO takes a POSITIVE viewpoint on the information submitted | 7
8 | 9 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is NEGATIVE | EAO takes a NEGATIVE viewpoint on the information submitted | 8
9 | 10 | EAC Extension Required | Start an EAC Extension WORK | An EAC Extension WORK is created for this PROJECT | 9
10 | 11 | EAC Cancellation Required | End SubStart and start EAC Cancellation | This "SubStart Determination" WORK is closed and an "EAC/Order Cancellation" WORK is created for this PROJECT | 10
11 | 12 | Delegation of SubStart Decision to Minister | Minister to Make SubStart Determination | The Decision Maker on this Substantial Start Determination will be the Minister | 11
12 | 13 | SubStart Determination Request Withdrawn | Holder Withdraws SubStart Determination Request | The Holder withdraws their Substantial Start Determination Request Application | 12
13 | 22 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is POSITIVE | EAO takes a POSITIVE viewpoint on the information submitted | 13
14 | 22 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is NEGATIVE | EAO takes a NEGATIVE viewpoint on the information submitted | 14
15 | 24 | EAC Extension Required | Start an EAC Extension WORK | An EAC Extension WORK is created for this PROJECT | 15
16 | 25 | EAC Cancellation Required | End SubStart and start EAC Cancellation | This "SubStart Determination" WORK is closed and an "EAC/Order Cancellation" WORK is created for this PROJECT | 16
17 | 36 | Delegation of SubStart Decision to Minister | Minister to Make SubStart Determination | The Decision Maker on this Substantial Start Determination will be the Minister | 17
18 | 37 | SubStart Determination Request Withdrawn | Holder Withdraws SubStart Determination Request | The Holder withdraws their Substantial Start Determination Request Application | 18
19 | 44 | SubStart Determination Request Withdrawn | Holder Withdraws SubStart Determination Request | The Holder withdraws their Substantial Start Determination Request Application | 19
20 | 48 | SubStart Determination Decision | Project is Substantially Started | The Decision Maker determines that the PROJECT has been SUBSTANTIALLY STARTED | 20
21 | 48 | SubStart Determination Decision | Project is Not Substantially Started | The Decision Maker determines that the PROJECT is NOT SUBSTANTIALLY STARTED | 21

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 1 | SubStart Initiated by Holder | NONE | No Actions Needed | {} | 1
2 | 2 | SubStart Initiated by C&E/Other | NONE | No Actions Needed | {} | 2
3 | 3 | SubStart Initiated by Deadline | NONE | No Actions Needed | {} | 3
4 | 4 | SubStart Determination is Not Needed | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 4
5 | 4 | SubStart Determination is Not Needed | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 5
6 | 4 | SubStart Determination is Not Needed | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 6
7 | 5 | SubStart Determination is Needed | NONE | No Actions Needed | {} | 7
8 | 6 | Delete the Pre-Assessment PHASE | SetEventDate | Set "SubStart Assessment ¦ SubStart Assessment Started" ANTICIPATED to thisWorkStartDate | {"phase_name":"SubStart Assessment","work_type_id": 10, "ea_act_id": 3, "event_name": "SubStart Assessment Started", "start_at": 0 } | 8
9 | 6 | Delete the Pre-Assessment PHASE | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 9
10 | 6 | Delete the Pre-Assessment PHASE | SetPhasesStatus | Set thisPhase to INACTIVE | [{"phase_name":"SubStart Pre-Assessment","work_type_id": 10, "ea_act_id": 3, "is_active": false }] | 10
11 | 7 | EAO's Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 11
12 | 8 | EAO's Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 12
13 | 9 | Start an EAC Extension WORK | CreateWork | createWork: "EAC Extension" and link to thisWorkLinkedProject | {"work_type": 9 } | 13
14 | 10 | End SubStart and start EAC Cancellation | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 14
15 | 10 | End SubStart and start EAC Cancellation | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 15
16 | 10 | End SubStart and start EAC Cancellation | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 16
17 | 10 | End SubStart and start EAC Cancellation | CreateWork | createWork: "EAC/Order Cancellation" and link to thisWorkLinkedProject | {"work_type": 13} | 17
18 | 11 | Minister to Make SubStart Determination | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentMinisterEnvironment | {"position_id": 8} | 18
19 | 12 | Holder Withdraws SubStart Determination Request | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 19
20 | 12 | Holder Withdraws SubStart Determination Request | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 20
21 | 12 | Holder Withdraws SubStart Determination Request | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 21
22 | 13 | EAO's Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 22
23 | 14 | EAO's Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 23
24 | 15 | Start an EAC Extension WORK | CreateWork | createWork: "EAC Extension" and link to thisWorkLinkedProject | {"work_type": 9 } | 24
25 | 16 | End SubStart and start EAC Cancellation | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 25
26 | 16 | End SubStart and start EAC Cancellation | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 26
27 | 16 | End SubStart and start EAC Cancellation | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 27
28 | 16 | End SubStart and start EAC Cancellation | CreateWork | createWork: "EAC/Order Cancellation" and link to thisWorkLinkedProject | {"work_type": 13} | 28
29 | 17 | Minister to Make SubStart Determination | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentMinisterEnvironment | {"position_id": 8} | 29
30 | 18 | Holder Withdraws SubStart Determination Request | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 30
31 | 18 | Holder Withdraws SubStart Determination Request | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 31
32 | 18 | Holder Withdraws SubStart Determination Request | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 32
33 | 19 | Holder Withdraws SubStart Determination Request | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 33
34 | 19 | Holder Withdraws SubStart Determination Request | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 34
35 | 19 | Holder Withdraws SubStart Determination Request | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 35
36 | 20 | Project is Substantially Started | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 36
37 | 20 | Project is Substantially Started | NONE | In the future this action should REMOVE the EAC CertificateEndDate | {} | 37
38 | 21 | Project is Not Substantially Started | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 38

## Lookups
WorkType | EA Act | Legislated |  | Event Type | Event Category | Visibility | ActionName | Event Position | Multiple Days | Action Name
Project Notification | EA Act (2018) | TRUE | Milestone | Generic | Milestone | MANDATORY | AllEventsDeactivated | START | TRUE | AddEvent
Minister's Designation | EA Act (2002) | FALSE | Milestone | Meeting | Calendar | SUGGESTED | AllEventsDeleted | INTERMEDIATE | FALSE | AddPhase
CEAO's Designation | EA Act (1996) |  | Milestone | Notification | Decision | OPTIONAL | CloseEverything | END |  | ChangePhaseEndEvent
EAC Assessment |  |  | Milestone | Order | Finance | HIDDEN | CloseWork |  |  | CreateWork
Exemption Request |  |  | Milestone | Referral | PCP |  | CompleteCurrentPhase |  |  | LockWorkStartDate
Dispute Resolution |  |  | Milestone | Report | Extension |  | CreateNewWork |  |  | SetEventDate
EAC/Order Amendment |  |  | Milestone | Request | Suspension |  | DisableWorkStartDate |  |  | SetEventStatus
Document Review |  |  | Milestone | Submission |  |  | DuplicatePhase |  |  | SetFederalInvolvement
EAC Extension |  |  | Milestone | Other | [5 empty] | SetPhaseStatus
Substantial Start Determination |  |  | Milestone | Date Capture | [5 empty] | SetProjectState
EAC/Order Transfer |  |  | Extension | Time Limit Extension | [5 empty] | SetProjectStatus
EAC/Order Suspension |  |  | Extension | PCP Time Limit Extension | [5 empty] | SetWorkDecisionMaker
EAC/Order Cancellation |  |  | Suspension | Time Limit Suspension | [5 empty] | SetWorkState
Other |  |  | Suspension | Time Limit Resumption
|  |  | Decision | EAC Ministers
|  |  | Decision | Minister
|  |  | Decision | CEAO
|  |  | Decision | ADM
|  |  | Decision | EPD
|  |  | Decision | PAD (Lead)
|  |  | Decision | Reviewer
|  |  | Decision | Federal
|  |  | Decision | Other
|  |  | PCP | Comment Period
|  |  | PCP | Open House
|  |  | PCP | Virtual Information Session
|  |  | PCP | Other
|  |  | Calendar | Communications
|  |  | Calendar | Executive
|  |  | Calendar | Financial
|  |  | Calendar | Work
|  |  | Calendar | Other
|  |  | Finance | Capacity Funding
|  |  | Finance | Fee Order
|  |  | Finance | Penalties
|  |  | Finance | Administrative
|  |  | Finance | Other